## Summary
metric | value
exported_at_ist | 2026-07-19 16:36:17
registry_path | /tmp/pytest-of-kamalji0501e/pytest-23/test_fixture_expiry_sheet0/registry.json
total_incidents | 22
closed | 22
open | 0
critical | 3
high | 16
fixture_expiry_sheet | See Fixture_Expiry tab for UAT book expiry + fix date commentary
commentary_sheet | See Commentary tab — issue, root cause, fix date, solution per incident

## Commentary
incident_id | title | date_observed | date_fixed | status | severity | priority | robot | category | subsystem | what_was_the_issue | root_cause | how_we_solved_it | validation_evidence | related_incidents | commentary
INC-2026-016 | Expired UAT fixture expiry blocks ShadowBroker bootstrap | 2026-06-25 | 2026-06-25 | closed | critical | p0 | kavach | broker | shadow_broker | Broker connect failed: No NIFTY PE strike 23500 for expiry 2026-06-23 in instrument master | uat/deployed_positions/positions.json retained past weekly expiry; instrument master drops expired series | resolve_fixture_trading_expiry() rolls to nearest valid weekly; ShadowBroker clears virtual ledger on roll | ShadowBroker.connect_with_token manual test; scripts/run_uat_e2e_verification.py ALL PASSED; 3-cycle ShadowBroker stress connect; pytest test_shadow_resolver | INC-2026-019 | Observed 2026-06-25: Broker connect failed: No NIFTY PE strike 23500 for expiry 2026-06-23 in instrument master ¦ Root cause: uat/deployed_positions/positions.json retained past weekly expiry; instrument master drops expired series ¦ Fixed 2026-06-25: resolve_fixture_trading_expiry() rolls to nearest valid weekly; ShadowBroker clears virtual ledger on roll ¦ Validated: ShadowBroker.connect_with_token manual test; scripts/run_uat_e2e_verification.py ALL PASSED; 3-cycle ShadowBroker stress connect; pytest test_shadow_resolver ¦ Lesson: UAT fixture expiry must roll or block with clear operator message; Virtual ledger must reset when core book expiry changes
INC-2026-017 | Mid-session WebSocket false failover — stale watchdog grace gap | 2026-06-25 | 2026-06-25 | closed | high | p1 | drishti | market_data | nifty_ltp_feed | WS connected at 10:46:02 then ATO auto-paused nifty_ltp_websocket_failed at 10:46:05 before first tick | Feed stale watchdog only applied 09:15 startup grace, not grace after mid-session WS reconnect when last_update_at is None | mark_transport_started() + is_within_transport_grace() — 30s grace after WS connect / REST service start | pytest test_feed_stale_watchdog_ws_transport_grace_after_reconnect | INC-2026-STAB-04; INC-2026-STAB-06 | Observed 2026-06-25: WS connected at 10:46:02 then ATO auto-paused nifty_ltp_websocket_failed at 10:46:05 before first tick ¦ Root cause: Feed stale watchdog only applied 09:15 startup grace, not grace after mid-session WS reconnect when last_update_at is None ¦ Fixed 2026-06-25: mark_transport_started() + is_within_transport_grace() — 30s grace after WS connect / REST service start ¦ Validated: pytest test_feed_stale_watchdog_ws_transport_grace_after_reconnect ¦ Lesson: Transport-level grace must cover reconnect, not only market open
INC-2026-018 | diagnose_robot.py reads wrong log root in UAT mode | 2026-06-25 | 2026-06-25 | closed | medium | p2 | drishti | documentation | observability | diagnose_robot reported 0 B all.log while bots were logging to logs_uat/ | Hardcoded logs/runtime path ignored batman_mode log_root | Use log_runtime_root(ROOT) from core.batman_mode | diagnose_robot.py kavach shows logs_uat paths and non-zero size |  | Observed 2026-06-25: diagnose_robot reported 0 B all.log while bots were logging to logs_uat/ ¦ Root cause: Hardcoded logs/runtime path ignored batman_mode log_root ¦ Fixed 2026-06-25: Use log_runtime_root(ROOT) from core.batman_mode ¦ Validated: diagnose_robot.py kavach shows logs_uat paths and non-zero size ¦ Lesson: All agent diagnostic tools must be mode-aware
INC-2026-019 | PE managed qty mismatch after partial virtual ledger on expiry roll | 2026-06-25 | 2026-06-25 | closed | high | p1 | kavach | testing | ato_protection | PE managed qty mismatch — broker=65 managed=130 after ATO auto CE protect | Stale shadow_order_ledger TRADED BUY PE 65 applied on top of rolled fixture before ledger clear fix | Clear virtual ledger when fixture expiry rolls forward | Post-fix KAVACH start — 4 legs PE netQty -130; ATO startup scan without PE halt | INC-2026-016 | Observed 2026-06-25: PE managed qty mismatch — broker=65 managed=130 after ATO auto CE protect ¦ Root cause: Stale shadow_order_ledger TRADED BUY PE 65 applied on top of rolled fixture before ledger clear fix ¦ Fixed 2026-06-25: Clear virtual ledger when fixture expiry rolls forward ¦ Validated: Post-fix KAVACH start — 4 legs PE netQty -130; ATO startup scan without PE halt
INC-2026-020 | UAT E2E log scan flagged pre-fix errors in same-day tail | 2026-06-25 | 2026-06-25 | closed | low | p3 |  | testing | uat_e2e | uat_log_scan FAIL with morning broker errors after afternoon fix | step_log_scan used full tail window without scoping to latest bot session | _current_session_lines() scans from last 'Batman mode:' startup marker | run_uat_e2e_verification.py uat_log_scan PASS |  | Observed 2026-06-25: uat_log_scan FAIL with morning broker errors after afternoon fix ¦ Root cause: step_log_scan used full tail window without scoping to latest bot session ¦ Fixed 2026-06-25: _current_session_lines() scans from last 'Batman mode:' startup marker ¦ Validated: run_uat_e2e_verification.py uat_log_scan PASS
INC-2026-021 | JAGRAN Telegram publish timeout during morning feed incident | 2026-06-25 | 2026-06-25 | closed | medium | p2 | jagran | connectivity | jagran | publish failed: Timed out at 10:50:54 IST during DRISHTI feed failover spam | Telegram API timeout while incident alerts flooded chat during WS/REST churn | No code change — transient; feed stabilization + sustained auto-resume reduces alert volume | JAGRAN logs post-11:15 show no further publish timeouts | INC-2026-STAB-04; INC-2026-022 | Observed 2026-06-25: publish failed: Timed out at 10:50:54 IST during DRISHTI feed failover spam ¦ Root cause: Telegram API timeout while incident alerts flooded chat during WS/REST churn ¦ Fixed 2026-06-25: No code change — transient; feed stabilization + sustained auto-resume reduces alert volume ¦ Validated: JAGRAN logs post-11:15 show no further publish timeouts ¦ Lesson: Correlate JAGRAN timeouts with upstream feed incidents before chasing bot bugs
INC-2026-022 | DRISHTI cold-start without JWT + ATO pause/resume churn after false WS failover | 2026-06-25 | 2026-06-25 | closed | high | p1 | drishti | connectivity | nifty_ltp_feed | Start All 10:43 without JWT until 10:44:52; false WS failover 10:46:05; ~25 min ATO pause/resume churn on nifty_ltp_feed_stale | Mid-session reconnect lacked transport grace (STAB-06 fix); on_feed_stale_cleared immediately resumed on brief fresh cache while REST was flaky | Transport grace on reconnect + AUTO_RESUME_STABLE_SECONDS=45 sustained can_auto_resume_feed_recovery before auto-resume | pytest test_feed_recovery sustained resume; Post-fix session no pause/resume churn in drishti logs | INC-2026-STAB-06; INC-2026-021 | Observed 2026-06-25: Start All 10:43 without JWT until 10:44:52; false WS failover 10:46:05; ~25 min ATO pause/resume churn on nifty_ltp_feed_stale ¦ Root cause: Mid-session reconnect lacked transport grace (STAB-06 fix); on_feed_stale_cleared immediately resumed on brief fresh cache while REST was flaky ¦ Fixed 2026-06-25: Transport grace on reconnect + AUTO_RESUME_STABLE_SECONDS=45 sustained can_auto_resume_feed_recovery before auto-resume ¦ Validated: pytest test_feed_recovery sustained resume; Post-fix session no pause/resume churn in drishti logs ¦ Lesson: Never auto-resume ATO on first stale_cleared tick — require sustained trading-ready cache
INC-2026-STAB-01 | UAT state-file split-brain — ATO pause written to wrong path | 2026-06-12 | 2026-06-12 | closed | high | p1 | kavach | configuration | algo_control | UAT state-file split-brain — ATO pause written to wrong path | pause_algo() used data/batman_state.json while UAT reads data/uat/batman_state.json | default_state_path() → state_path(workspace_root()) mode-aware | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | INC-2026-STAB-02 | Observed 2026-06-12: UAT state-file split-brain — ATO pause written to wrong path ¦ Root cause: pause_algo() used data/batman_state.json while UAT reads data/uat/batman_state.json ¦ Fixed 2026-06-12: default_state_path() → state_path(workspace_root()) mode-aware ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check ¦ Lesson: All cross-bot state writes must use state_path() — never hard-code data/
INC-2026-STAB-02 | KAVACH menu reads wrong pause state in UAT | 2026-06-12 | 2026-06-12 | closed | high | p1 | kavach | robot |  | KAVACH menu reads wrong pause state in UAT | _read_algo_pause_reason() used default StateManager path | Use state_path(workspace_root()) | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | INC-2026-STAB-01 | Observed 2026-06-12: KAVACH menu reads wrong pause state in UAT ¦ Root cause: _read_algo_pause_reason() used default StateManager path ¦ Fixed 2026-06-12: Use state_path(workspace_root()) ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-03 | Failover state lost on DRISHTI restart | 2026-06-12 | 2026-06-12 | closed | high | p1 | drishti | market_data |  | Failover state lost on DRISHTI restart | WS→REST session lock lived only in app.bot_data | Persist failover to batman_state.json key nifty_ltp_failover | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: Failover state lost on DRISHTI restart ¦ Root cause: WS→REST session lock lived only in app.bot_data ¦ Fixed 2026-06-12: Persist failover to batman_state.json key nifty_ltp_failover ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-04 | WebSocket Previous Close frame treated as fatal error | 2026-06-12 | 2026-06-12 | closed | critical | p0 | drishti | market_data |  | WebSocket Previous Close frame treated as fatal error | Dhan v2 control frame without LTP triggered reconnect loop | extract_ltp_from_ws_tick skips non-LTP control frames | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | INC-2026-017 | Observed 2026-06-12: WebSocket Previous Close frame treated as fatal error ¦ Root cause: Dhan v2 control frame without LTP triggered reconnect loop ¦ Fixed 2026-06-12: extract_ltp_from_ws_tick skips non-LTP control frames ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-05 | WebSocket HTTP 429 reconnect storm | 2026-06-12 | 2026-06-12 | closed | critical | p0 | drishti | market_data |  | WebSocket HTTP 429 reconnect storm | 429 incremented failure counter → false failover | 429 cooldown; do not increment consecutive_failures | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | INC-2026-STAB-06 | Observed 2026-06-12: WebSocket HTTP 429 reconnect storm ¦ Root cause: 429 incremented failure counter → false failover ¦ Fixed 2026-06-12: 429 cooldown; do not increment consecutive_failures ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-06 | WS 429 cooldown exceeded stale threshold → false failover | 2026-06-12 | 2026-06-12 | closed | high | p1 | drishti | market_data |  | WS 429 cooldown exceeded stale threshold → false failover | Stale watchdog ignored rate_limit_until during cooldown | Skip stale alerts during rate-limit cooldown; refresh last_update_at on 429 | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | INC-2026-017; INC-2026-STAB-05 | Observed 2026-06-12: WS 429 cooldown exceeded stale threshold → false failover ¦ Root cause: Stale watchdog ignored rate_limit_until during cooldown ¦ Fixed 2026-06-12: Skip stale alerts during rate-limit cooldown; refresh last_update_at on 429 ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-07 | Feed gating used save-age only, not JWT exp | 2026-06-12 | 2026-06-12 | closed | high | p1 | drishti | broker |  | Feed gating used save-age only, not JWT exp | is_expired() vs effective JWT expiry mismatch | is_effectively_expired() gates feed start | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: Feed gating used save-age only, not JWT exp ¦ Root cause: is_expired() vs effective JWT expiry mismatch ¦ Fixed 2026-06-12: is_effectively_expired() gates feed start ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-08 | Startup lock / PID reuse failures | 2026-06-12 | 2026-06-12 | closed | high | p1 |  | infrastructure |  | Startup lock / PID reuse failures | Plain PID locks; UAT lock path mismatch | Tier 1+2 lifecycle hardening + reconcile | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: Startup lock / PID reuse failures ¦ Root cause: Plain PID locks; UAT lock path mismatch ¦ Fixed 2026-06-12: Tier 1+2 lifecycle hardening + reconcile ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-09 | Auth errors retried and triggered failover | 2026-06-12 | 2026-06-12 | closed | high | p1 | drishti | broker |  | Auth errors retried and triggered failover | HTTP 401 treated as connection error | is_auth_error() + on_auth_failure — no retry, no failover | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: Auth errors retried and triggered failover ¦ Root cause: HTTP 401 treated as connection error ¦ Fixed 2026-06-12: is_auth_error() + on_auth_failure — no retry, no failover ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-10 | KAVACH cold-start without JWT | 2026-06-12 | 2026-06-12 | closed | high | p1 | kavach | robot |  | KAVACH cold-start without JWT | token_watch skipped when broker was None at startup | Lazy bootstrap via on_token_ready callback | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: KAVACH cold-start without JWT ¦ Root cause: token_watch skipped when broker was None at startup ¦ Fixed 2026-06-12: Lazy bootstrap via on_token_ready callback ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-11 | Supervisor ignored LTP gate failure | 2026-06-12 | 2026-06-12 | closed | high | p1 |  | infrastructure |  | Supervisor ignored LTP gate failure | LTP gate logged WARN only during market session | Abort Start All when LTP gate fails | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: Supervisor ignored LTP gate failure ¦ Root cause: LTP gate logged WARN only during market session ¦ Fixed 2026-06-12: Abort Start All when LTP gate fails ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-12 | health.json not authoritative for RUNNING | 2026-06-12 | 2026-06-12 | closed | high | p1 |  | infrastructure |  | health.json not authoritative for RUNNING | classify_bot() ignored health heartbeat file | health_confirms_running() upgrades status; stale heartbeat warnings | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: health.json not authoritative for RUNNING ¦ Root cause: classify_bot() ignored health heartbeat file ¦ Fixed 2026-06-12: health_confirms_running() upgrades status; stale heartbeat warnings ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-13 | Session REST lock with no same-day WS retry | 2026-06-12 | 2026-06-12 | closed | high | p1 | drishti | market_data |  | Session REST lock with no same-day WS retry | session_rest_lock_date blocked WS without retry path | try_websocket_retry_after_rest() every 15 min | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: Session REST lock with no same-day WS retry ¦ Root cause: session_rest_lock_date blocked WS without retry path ¦ Fixed 2026-06-12: try_websocket_retry_after_rest() every 15 min ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-14 | Live Price opened parallel one-shot WebSocket | 2026-06-12 | 2026-06-12 | closed | high | p1 | drishti | market_data |  | Live Price opened parallel one-shot WebSocket | Handler always opened new WS while background feed active | Prefer fresh cache when background feed healthy | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: Live Price opened parallel one-shot WebSocket ¦ Root cause: Handler always opened new WS while background feed active ¦ Fixed 2026-06-12: Prefer fresh cache when background feed healthy ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-15 | Lock timeout without retry on state writes | 2026-06-12 | 2026-06-12 | closed | high | p1 |  | runtime |  | Lock timeout without retry on state writes | exclusive_file_lock() single attempt under concurrent writes | retries=3 with backoff on TimeoutError; state.save mkdir parent | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check |  | Observed 2026-06-12: Lock timeout without retry on state writes ¦ Root cause: exclusive_file_lock() single attempt under concurrent writes ¦ Fixed 2026-06-12: retries=3 with backoff on TimeoutError; state.save mkdir parent ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check

## All_Issues
incident_id | title | category | subsystem | robot_affected | date_first_observed | date_resolved | lifecycle | severity | priority | environment | frequency | symptoms | business_impact | technical_impact | trading_impact | root_cause | contributing_factors | investigation | files_modules | logs_referenced | fix_implemented | fix_rationale | regression_risk | validation_performed | stress_testing | validation_cycles | remaining_risks | related_incidents | runtime_incident_ids | preventive_measures | lessons_learned | future_recommendations | owner | last_updated | tags
INC-2026-016 | Expired UAT fixture expiry blocks ShadowBroker bootstrap | broker | shadow_broker | kavach | 2026-06-25 | 2026-06-25 | closed | critical | p0 | uat | daily_after_weekly_expiry | Broker connect failed: No NIFTY PE strike 23500 for expiry 2026-06-23 in instrument master | KAVACH and SARANSH could not load virtual positions; /register and /positions broken | create_broker() raised LookupError during ShadowBroker._reload_positions_from_fixture | ATO module did not start; no mock order flow | uat/deployed_positions/positions.json retained past weekly expiry; instrument master drops expired series | Fixture captured 2026-06-13 for 23 Jun expiry; No auto-roll on weekly expiry boundary | logs_uat/.../kavach/errors/all_errors.log 10:46 IST; incident CSV kavach::log_error | backtest_engine/shadow/shadow_broker.py; backtest_engine/resolver/instrument_master.py; uat/deployed_positions/positions.json | logs_uat/runtime/2026-06/2026-06-25/kavach/errors/all_errors.log; data/analytics/incidents/by_domain/kavach/incidents_20260625.csv | resolve_fixture_trading_expiry() rolls to nearest valid weekly; ShadowBroker clears virtual ledger on roll | UAT book remains loadable without manual fixture edit every expiry day; stale virtual fills cannot corrupt qty | New weekly expiry without strikes in master may still fail — operator should refresh screenshot | ShadowBroker.connect_with_token manual test; scripts/run_uat_e2e_verification.py ALL PASSED; 3-cycle ShadowBroker stress connect; pytest test_shadow_resolver | 3-cycle broker connect loop | 3 | Operator fixture still shows 23 Jun label until new screenshot ingested | INC-2026-019 | kavach::log_error | Refresh Sensibull screenshot after weekly expiry; Run validate_fixture.py after positions.json change | UAT fixture expiry must roll or block with clear operator message; Virtual ledger must reset when core book expiry changes | Optional Telegram reminder on expiry day if fixture age > 5 days | agent |  | uat; shadow-broker; closed
INC-2026-017 | Mid-session WebSocket false failover — stale watchdog grace gap | market_data | nifty_ltp_feed | drishti | 2026-06-25 | 2026-06-25 | closed | high | p1 | uat | on_ws_reconnect_after_0930 | WS connected at 10:46:02 then ATO auto-paused nifty_ltp_websocket_failed at 10:46:05 before first tick |  | on_feed_stale → on_websocket_crash → REST fallback + algo pause cascade | ATO paused repeatedly with nifty_ltp_feed_stale warnings | Feed stale watchdog only applied 09:15 startup grace, not grace after mid-session WS reconnect when last_update_at is None | consumer_max_age_seconds=5; WS connect-to-first-tick latency | logs_uat/.../drishti/logs/all.log lines 104602–104605 IST | core/nifty_ltp_feed.py; core/nifty_ltp_websocket_feed.py; bat_telegram/bots/drishti/nifty_feed_integration.py | logs_uat/runtime/2026-06/2026-06-25/drishti/logs/all.log | mark_transport_started() + is_within_transport_grace() — 30s grace after WS connect / REST service start | Distinguishes cold reconnect from true feed death | Very slow first tick (>30s) could still false-positive — monitor ws_ltp audit log | pytest test_feed_stale_watchdog_ws_transport_grace_after_reconnect |  | 2 |  | INC-2026-STAB-04; INC-2026-STAB-06 |  |  | Transport-level grace must cover reconnect, not only market open |  | agent |  | websocket; closed
INC-2026-018 | diagnose_robot.py reads wrong log root in UAT mode | documentation | observability | drishti | 2026-06-25 | 2026-06-25 | closed | medium | p2 | uat | once | diagnose_robot reported 0 B all.log while bots were logging to logs_uat/ |  |  |  | Hardcoded logs/runtime path ignored batman_mode log_root |  |  | scripts/diagnose_robot.py |  | Use log_runtime_root(ROOT) from core.batman_mode |  |  | diagnose_robot.py kavach shows logs_uat paths and non-zero size |  | 1 |  |  |  |  | All agent diagnostic tools must be mode-aware |  | agent |  | observability; closed
INC-2026-019 | PE managed qty mismatch after partial virtual ledger on expiry roll | testing | ato_protection | kavach | 2026-06-25 | 2026-06-25 | closed | high | p1 | uat | once | PE managed qty mismatch — broker=65 managed=130 after ATO auto CE protect |  |  |  | Stale shadow_order_ledger TRADED BUY PE 65 applied on top of rolled fixture before ledger clear fix |  |  | backtest_engine/shadow/shadow_broker.py; data/uat/shadow_order_ledger.json; modules/ato_protection.py |  | Clear virtual ledger when fixture expiry rolls forward |  |  | Post-fix KAVACH start — 4 legs PE netQty -130; ATO startup scan without PE halt |  | 2 |  | INC-2026-016 |  |  |  |  | agent |  | uat; ato; closed
INC-2026-020 | UAT E2E log scan flagged pre-fix errors in same-day tail | testing | uat_e2e |  | 2026-06-25 | 2026-06-25 | closed | low | p3 | uat | once | uat_log_scan FAIL with morning broker errors after afternoon fix |  |  |  | step_log_scan used full tail window without scoping to latest bot session |  |  | scripts/run_uat_e2e_verification.py |  | _current_session_lines() scans from last 'Batman mode:' startup marker |  |  | run_uat_e2e_verification.py uat_log_scan PASS |  | 2 | [6 empty] | agent |  | testing; closed
INC-2026-021 | JAGRAN Telegram publish timeout during morning feed incident | connectivity | jagran | jagran | 2026-06-25 | 2026-06-25 | closed | medium | p2 | uat | once | publish failed: Timed out at 10:50:54 IST during DRISHTI feed failover spam |  |  |  | Telegram API timeout while incident alerts flooded chat during WS/REST churn |  |  | bat_telegram/bots/jagran/ |  | No code change — transient; feed stabilization + sustained auto-resume reduces alert volume |  |  | JAGRAN logs post-11:15 show no further publish timeouts |  | 1 |  | INC-2026-STAB-04; INC-2026-022 |  |  | Correlate JAGRAN timeouts with upstream feed incidents before chasing bot bugs |  | agent |  | telegram; closed
INC-2026-022 | DRISHTI cold-start without JWT + ATO pause/resume churn after false WS failover | connectivity | nifty_ltp_feed | drishti | 2026-06-25 | 2026-06-25 | closed | high | p1 | uat | once | Start All 10:43 without JWT until 10:44:52; false WS failover 10:46:05; ~25 min ATO pause/resume churn on nifty_ltp_feed_stale |  |  |  | Mid-session reconnect lacked transport grace (STAB-06 fix); on_feed_stale_cleared immediately resumed on brief fresh cache while REST was flaky |  |  | core/nifty_ltp_feed.py; core/nifty_ltp_websocket_feed.py; core/feed_recovery.py; bat_telegram/bots/drishti/nifty_feed_integration.py |  | Transport grace on reconnect + AUTO_RESUME_STABLE_SECONDS=45 sustained can_auto_resume_feed_recovery before auto-resume |  |  | pytest test_feed_recovery sustained resume; Post-fix session no pause/resume churn in drishti logs |  | 2 |  | INC-2026-STAB-06; INC-2026-021 |  |  | Never auto-resume ATO on first stale_cleared tick — require sustained trading-ready cache |  | agent |  | websocket; ato; closed
INC-2026-STAB-01 | UAT state-file split-brain — ATO pause written to wrong path | configuration | algo_control | kavach | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | UAT state-file split-brain — ATO pause written to wrong path |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | pause_algo() used data/batman_state.json while UAT reads data/uat/batman_state.json |  |  | core/algo_control.py; core/feed_recovery.py |  | default_state_path() → state_path(workspace_root()) mode-aware | default_state_path() → state_path(workspace_root()) mode-aware | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 |  | INC-2026-STAB-02 |  | All cross-bot state writes must use state_path() — never hard-code data/ | All cross-bot state writes must use state_path() — never hard-code data/ |  | agent |  | stabilization-sprint; closed
INC-2026-STAB-02 | KAVACH menu reads wrong pause state in UAT | robot |  | kavach | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | KAVACH menu reads wrong pause state in UAT |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | _read_algo_pause_reason() used default StateManager path |  |  | bat_telegram/bots/kavach/bot.py |  | Use state_path(workspace_root()) | Use state_path(workspace_root()) | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 |  | INC-2026-STAB-01 |  |  |  |  | agent |  | stabilization-sprint; closed
INC-2026-STAB-03 | Failover state lost on DRISHTI restart | market_data |  | drishti | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | Failover state lost on DRISHTI restart |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | WS→REST session lock lived only in app.bot_data |  |  | core/nifty_ltp_failover.py |  | Persist failover to batman_state.json key nifty_ltp_failover | Persist failover to batman_state.json key nifty_ltp_failover | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-04 | WebSocket Previous Close frame treated as fatal error | market_data |  | drishti | 2026-06-12 | 2026-06-12 | closed | critical | p0 | uat | intermittent | WebSocket Previous Close frame treated as fatal error |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | Dhan v2 control frame without LTP triggered reconnect loop |  |  | core/dhan_ws_tick.py; core/nifty_ltp_websocket_feed.py |  | extract_ltp_from_ws_tick skips non-LTP control frames | extract_ltp_from_ws_tick skips non-LTP control frames | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 |  | INC-2026-017 |  |  |  |  | agent |  | stabilization-sprint; closed
INC-2026-STAB-05 | WebSocket HTTP 429 reconnect storm | market_data |  | drishti | 2026-06-12 | 2026-06-12 | closed | critical | p0 | uat | intermittent | WebSocket HTTP 429 reconnect storm |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | 429 incremented failure counter → false failover |  |  | core/nifty_ltp_websocket_feed.py |  | 429 cooldown; do not increment consecutive_failures | 429 cooldown; do not increment consecutive_failures | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 |  | INC-2026-STAB-06 |  |  |  |  | agent |  | stabilization-sprint; closed
INC-2026-STAB-06 | WS 429 cooldown exceeded stale threshold → false failover | market_data |  | drishti | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | WS 429 cooldown exceeded stale threshold → false failover |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | Stale watchdog ignored rate_limit_until during cooldown |  |  | core/nifty_ltp_feed.py; core/nifty_ltp_websocket_feed.py |  | Skip stale alerts during rate-limit cooldown; refresh last_update_at on 429 | Skip stale alerts during rate-limit cooldown; refresh last_update_at on 429 | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 |  | INC-2026-017; INC-2026-STAB-05 |  |  |  |  | agent |  | stabilization-sprint; closed
INC-2026-STAB-07 | Feed gating used save-age only, not JWT exp | broker |  | drishti | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | Feed gating used save-age only, not JWT exp |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | is_expired() vs effective JWT expiry mismatch |  |  | core/token_store.py; bat_telegram/bots/drishti/nifty_feed_integration.py |  | is_effectively_expired() gates feed start | is_effectively_expired() gates feed start | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-08 | Startup lock / PID reuse failures | infrastructure |  |  | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | Startup lock / PID reuse failures |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | Plain PID locks; UAT lock path mismatch |  |  | core/instance_lock.py; core/bot_lifecycle.py; core/bot_supervisor.py |  | Tier 1+2 lifecycle hardening + reconcile | Tier 1+2 lifecycle hardening + reconcile | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-09 | Auth errors retried and triggered failover | broker |  | drishti | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | Auth errors retried and triggered failover |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | HTTP 401 treated as connection error |  |  | core/nifty_ltp.py; core/nifty_ltp_feed.py; core/nifty_ltp_websocket_feed.py |  | is_auth_error() + on_auth_failure — no retry, no failover | is_auth_error() + on_auth_failure — no retry, no failover | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-10 | KAVACH cold-start without JWT | robot |  | kavach | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | KAVACH cold-start without JWT |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | token_watch skipped when broker was None at startup |  |  | core/token_watch.py; run_kavach.py |  | Lazy bootstrap via on_token_ready callback | Lazy bootstrap via on_token_ready callback | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-11 | Supervisor ignored LTP gate failure | infrastructure |  |  | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | Supervisor ignored LTP gate failure |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | LTP gate logged WARN only during market session |  |  | core/bot_supervisor.py |  | Abort Start All when LTP gate fails | Abort Start All when LTP gate fails | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-12 | health.json not authoritative for RUNNING | infrastructure |  |  | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | health.json not authoritative for RUNNING |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | classify_bot() ignored health heartbeat file |  |  | core/bot_health.py; core/bot_process_status.py |  | health_confirms_running() upgrades status; stale heartbeat warnings | health_confirms_running() upgrades status; stale heartbeat warnings | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-13 | Session REST lock with no same-day WS retry | market_data |  | drishti | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | Session REST lock with no same-day WS retry |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | session_rest_lock_date blocked WS without retry path |  |  | core/nifty_ltp_failover.py; bat_telegram/bots/drishti/nifty_feed_integration.py |  | try_websocket_retry_after_rest() every 15 min | try_websocket_retry_after_rest() every 15 min | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-14 | Live Price opened parallel one-shot WebSocket | market_data |  | drishti | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | Live Price opened parallel one-shot WebSocket |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | Handler always opened new WS while background feed active |  |  | bat_telegram/bots/drishti/nifty_feed_integration.py |  | Prefer fresh cache when background feed healthy | Prefer fresh cache when background feed healthy | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed
INC-2026-STAB-15 | Lock timeout without retry on state writes | runtime |  |  | 2026-06-12 | 2026-06-12 | closed | high | p1 | uat | intermittent | Lock timeout without retry on state writes |  | Phase 1 reliability / feed / lifecycle | ATO may not pause/resume correctly; feed outages; orphan processes | exclusive_file_lock() single attempt under concurrent writes |  |  | core/process_lock.py; core/state.py |  | retries=3 with backoff on TimeoutError; state.save mkdir parent | retries=3 with backoff on TimeoutError; state.save mkdir parent | Re-test on UAT mode + feed failover after changes to listed modules | pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check | 3-cycle stabilization_verify | 3 | [6 empty] | agent |  | stabilization-sprint; closed

## Fixture_Expiry
field | value
fixture_path | uat/deployed_positions/positions.json
expiry_label_in_fixture | 21 Jul 2026
expiry_date_in_fixture | 2026-07-21
captured_at | 2026-07-17T18:46:01.622565+00:00
leg_count | 4
resolved_trading_expiry | 2026-07-21
auto_roll_active | no
code_fix_date | 2026-06-25
linked_incident | INC-2026-016
what_was_the_issue | Broker connect failed: No NIFTY PE strike 23500 for expiry 2026-06-23 in instrument master
how_we_solved_it | resolve_fixture_trading_expiry() rolls to nearest valid weekly; ShadowBroker clears virtual ledger on roll
commentary | Fixture file still shows 21 Jul 2026 (captured 2026-07-17). Code fix dated 2026-06-25 auto-rolls trading to 2026-07-21 when file expiry is past. Operator should refresh Sensibull screenshot after each weekly expiry so label matches live book.
operator_action | Refresh uat/deployed_positions screenshot after weekly NIFTY expiry

## By_Robot
robot | incident_id | date_observed | date_fixed | severity | title | status | commentary
kavach | INC-2026-016 | 2026-06-25 | 2026-06-25 | critical | Expired UAT fixture expiry blocks ShadowBroker bootstrap | closed | Observed 2026-06-25: Broker connect failed: No NIFTY PE strike 23500 for expiry 2026-06-23 in instrument master ¦ Root cause: uat/deployed_positions/positions.json retained past weekly expiry; instrument master drops expired series ¦ Fixed 2026-06-25: resolve_fixture_trading_expiry() rolls to nearest valid weekly; ShadowBroker clears virtual ledger on roll ¦ Validated: ShadowBroker.connect_with_token manual test; scripts/run_uat_e2e_verification.py ALL PASSED; 3-cycle ShadowBroker stress connect; pytest test_shadow_resolver ¦ Lesson: UAT fixture expiry must roll or block with clear operator message; Virtual ledger must reset when core book expiry changes
drishti | INC-2026-017 | 2026-06-25 | 2026-06-25 | high | Mid-session WebSocket false failover — stale watchdog grace gap | closed | Observed 2026-06-25: WS connected at 10:46:02 then ATO auto-paused nifty_ltp_websocket_failed at 10:46:05 before first tick ¦ Root cause: Feed stale watchdog only applied 09:15 startup grace, not grace after mid-session WS reconnect when last_update_at is None ¦ Fixed 2026-06-25: mark_transport_started() + is_within_transport_grace() — 30s grace after WS connect / REST service start ¦ Validated: pytest test_feed_stale_watchdog_ws_transport_grace_after_reconnect ¦ Lesson: Transport-level grace must cover reconnect, not only market open
drishti | INC-2026-018 | 2026-06-25 | 2026-06-25 | medium | diagnose_robot.py reads wrong log root in UAT mode | closed | Observed 2026-06-25: diagnose_robot reported 0 B all.log while bots were logging to logs_uat/ ¦ Root cause: Hardcoded logs/runtime path ignored batman_mode log_root ¦ Fixed 2026-06-25: Use log_runtime_root(ROOT) from core.batman_mode ¦ Validated: diagnose_robot.py kavach shows logs_uat paths and non-zero size ¦ Lesson: All agent diagnostic tools must be mode-aware
kavach | INC-2026-019 | 2026-06-25 | 2026-06-25 | high | PE managed qty mismatch after partial virtual ledger on expiry roll | closed | Observed 2026-06-25: PE managed qty mismatch — broker=65 managed=130 after ATO auto CE protect ¦ Root cause: Stale shadow_order_ledger TRADED BUY PE 65 applied on top of rolled fixture before ledger clear fix ¦ Fixed 2026-06-25: Clear virtual ledger when fixture expiry rolls forward ¦ Validated: Post-fix KAVACH start — 4 legs PE netQty -130; ATO startup scan without PE halt
(system) | INC-2026-020 | 2026-06-25 | 2026-06-25 | low | UAT E2E log scan flagged pre-fix errors in same-day tail | closed | Observed 2026-06-25: uat_log_scan FAIL with morning broker errors after afternoon fix ¦ Root cause: step_log_scan used full tail window without scoping to latest bot session ¦ Fixed 2026-06-25: _current_session_lines() scans from last 'Batman mode:' startup marker ¦ Validated: run_uat_e2e_verification.py uat_log_scan PASS
jagran | INC-2026-021 | 2026-06-25 | 2026-06-25 | medium | JAGRAN Telegram publish timeout during morning feed incident | closed | Observed 2026-06-25: publish failed: Timed out at 10:50:54 IST during DRISHTI feed failover spam ¦ Root cause: Telegram API timeout while incident alerts flooded chat during WS/REST churn ¦ Fixed 2026-06-25: No code change — transient; feed stabilization + sustained auto-resume reduces alert volume ¦ Validated: JAGRAN logs post-11:15 show no further publish timeouts ¦ Lesson: Correlate JAGRAN timeouts with upstream feed incidents before chasing bot bugs
drishti | INC-2026-022 | 2026-06-25 | 2026-06-25 | high | DRISHTI cold-start without JWT + ATO pause/resume churn after false WS failover | closed | Observed 2026-06-25: Start All 10:43 without JWT until 10:44:52; false WS failover 10:46:05; ~25 min ATO pause/resume churn on nifty_ltp_feed_stale ¦ Root cause: Mid-session reconnect lacked transport grace (STAB-06 fix); on_feed_stale_cleared immediately resumed on brief fresh cache while REST was flaky ¦ Fixed 2026-06-25: Transport grace on reconnect + AUTO_RESUME_STABLE_SECONDS=45 sustained can_auto_resume_feed_recovery before auto-resume ¦ Validated: pytest test_feed_recovery sustained resume; Post-fix session no pause/resume churn in drishti logs ¦ Lesson: Never auto-resume ATO on first stale_cleared tick — require sustained trading-ready cache
kavach | INC-2026-STAB-01 | 2026-06-12 | 2026-06-12 | high | UAT state-file split-brain — ATO pause written to wrong path | closed | Observed 2026-06-12: UAT state-file split-brain — ATO pause written to wrong path ¦ Root cause: pause_algo() used data/batman_state.json while UAT reads data/uat/batman_state.json ¦ Fixed 2026-06-12: default_state_path() → state_path(workspace_root()) mode-aware ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check ¦ Lesson: All cross-bot state writes must use state_path() — never hard-code data/
kavach | INC-2026-STAB-02 | 2026-06-12 | 2026-06-12 | high | KAVACH menu reads wrong pause state in UAT | closed | Observed 2026-06-12: KAVACH menu reads wrong pause state in UAT ¦ Root cause: _read_algo_pause_reason() used default StateManager path ¦ Fixed 2026-06-12: Use state_path(workspace_root()) ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
drishti | INC-2026-STAB-03 | 2026-06-12 | 2026-06-12 | high | Failover state lost on DRISHTI restart | closed | Observed 2026-06-12: Failover state lost on DRISHTI restart ¦ Root cause: WS→REST session lock lived only in app.bot_data ¦ Fixed 2026-06-12: Persist failover to batman_state.json key nifty_ltp_failover ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
drishti | INC-2026-STAB-04 | 2026-06-12 | 2026-06-12 | critical | WebSocket Previous Close frame treated as fatal error | closed | Observed 2026-06-12: WebSocket Previous Close frame treated as fatal error ¦ Root cause: Dhan v2 control frame without LTP triggered reconnect loop ¦ Fixed 2026-06-12: extract_ltp_from_ws_tick skips non-LTP control frames ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
drishti | INC-2026-STAB-05 | 2026-06-12 | 2026-06-12 | critical | WebSocket HTTP 429 reconnect storm | closed | Observed 2026-06-12: WebSocket HTTP 429 reconnect storm ¦ Root cause: 429 incremented failure counter → false failover ¦ Fixed 2026-06-12: 429 cooldown; do not increment consecutive_failures ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
drishti | INC-2026-STAB-06 | 2026-06-12 | 2026-06-12 | high | WS 429 cooldown exceeded stale threshold → false failover | closed | Observed 2026-06-12: WS 429 cooldown exceeded stale threshold → false failover ¦ Root cause: Stale watchdog ignored rate_limit_until during cooldown ¦ Fixed 2026-06-12: Skip stale alerts during rate-limit cooldown; refresh last_update_at on 429 ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
drishti | INC-2026-STAB-07 | 2026-06-12 | 2026-06-12 | high | Feed gating used save-age only, not JWT exp | closed | Observed 2026-06-12: Feed gating used save-age only, not JWT exp ¦ Root cause: is_expired() vs effective JWT expiry mismatch ¦ Fixed 2026-06-12: is_effectively_expired() gates feed start ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
(system) | INC-2026-STAB-08 | 2026-06-12 | 2026-06-12 | high | Startup lock / PID reuse failures | closed | Observed 2026-06-12: Startup lock / PID reuse failures ¦ Root cause: Plain PID locks; UAT lock path mismatch ¦ Fixed 2026-06-12: Tier 1+2 lifecycle hardening + reconcile ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
drishti | INC-2026-STAB-09 | 2026-06-12 | 2026-06-12 | high | Auth errors retried and triggered failover | closed | Observed 2026-06-12: Auth errors retried and triggered failover ¦ Root cause: HTTP 401 treated as connection error ¦ Fixed 2026-06-12: is_auth_error() + on_auth_failure — no retry, no failover ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
kavach | INC-2026-STAB-10 | 2026-06-12 | 2026-06-12 | high | KAVACH cold-start without JWT | closed | Observed 2026-06-12: KAVACH cold-start without JWT ¦ Root cause: token_watch skipped when broker was None at startup ¦ Fixed 2026-06-12: Lazy bootstrap via on_token_ready callback ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
(system) | INC-2026-STAB-11 | 2026-06-12 | 2026-06-12 | high | Supervisor ignored LTP gate failure | closed | Observed 2026-06-12: Supervisor ignored LTP gate failure ¦ Root cause: LTP gate logged WARN only during market session ¦ Fixed 2026-06-12: Abort Start All when LTP gate fails ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
(system) | INC-2026-STAB-12 | 2026-06-12 | 2026-06-12 | high | health.json not authoritative for RUNNING | closed | Observed 2026-06-12: health.json not authoritative for RUNNING ¦ Root cause: classify_bot() ignored health heartbeat file ¦ Fixed 2026-06-12: health_confirms_running() upgrades status; stale heartbeat warnings ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
drishti | INC-2026-STAB-13 | 2026-06-12 | 2026-06-12 | high | Session REST lock with no same-day WS retry | closed | Observed 2026-06-12: Session REST lock with no same-day WS retry ¦ Root cause: session_rest_lock_date blocked WS without retry path ¦ Fixed 2026-06-12: try_websocket_retry_after_rest() every 15 min ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
drishti | INC-2026-STAB-14 | 2026-06-12 | 2026-06-12 | high | Live Price opened parallel one-shot WebSocket | closed | Observed 2026-06-12: Live Price opened parallel one-shot WebSocket ¦ Root cause: Handler always opened new WS while background feed active ¦ Fixed 2026-06-12: Prefer fresh cache when background feed healthy ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
(system) | INC-2026-STAB-15 | 2026-06-12 | 2026-06-12 | high | Lock timeout without retry on state writes | closed | Observed 2026-06-12: Lock timeout without retry on state writes ¦ Root cause: exclusive_file_lock() single attempt under concurrent writes ¦ Fixed 2026-06-12: retries=3 with backoff on TimeoutError; state.save mkdir parent ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check

## Related_Incidents
incident_id | related_incident_id | title | date_fixed | commentary
INC-2026-016 | INC-2026-019 | PE managed qty mismatch after partial virtual ledger on expiry roll | 2026-06-25 | Observed 2026-06-25: PE managed qty mismatch — broker=65 managed=130 after ATO auto CE protect ¦ Root cause: Stale shadow_order_ledger TRADED BUY PE 65 applied on top of rolled fixture before ledger clear fix ¦ Fixed 2026-06-25: Clear virtual ledger when fixture expiry rolls forward ¦ Validated: Post-fix KAVACH start — 4 legs PE netQty -130; ATO startup scan without PE halt
INC-2026-017 | INC-2026-STAB-04 | WebSocket Previous Close frame treated as fatal error | 2026-06-12 | Observed 2026-06-12: WebSocket Previous Close frame treated as fatal error ¦ Root cause: Dhan v2 control frame without LTP triggered reconnect loop ¦ Fixed 2026-06-12: extract_ltp_from_ws_tick skips non-LTP control frames ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-017 | INC-2026-STAB-06 | WS 429 cooldown exceeded stale threshold → false failover | 2026-06-12 | Observed 2026-06-12: WS 429 cooldown exceeded stale threshold → false failover ¦ Root cause: Stale watchdog ignored rate_limit_until during cooldown ¦ Fixed 2026-06-12: Skip stale alerts during rate-limit cooldown; refresh last_update_at on 429 ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-019 | INC-2026-016 | Expired UAT fixture expiry blocks ShadowBroker bootstrap | 2026-06-25 | Observed 2026-06-25: Broker connect failed: No NIFTY PE strike 23500 for expiry 2026-06-23 in instrument master ¦ Root cause: uat/deployed_positions/positions.json retained past weekly expiry; instrument master drops expired series ¦ Fixed 2026-06-25: resolve_fixture_trading_expiry() rolls to nearest valid weekly; ShadowBroker clears virtual ledger on roll ¦ Validated: ShadowBroker.connect_with_token manual test; scripts/run_uat_e2e_verification.py ALL PASSED; 3-cycle ShadowBroker stress connect; pytest test_shadow_resolver ¦ Lesson: UAT fixture expiry must roll or block with clear operator message; Virtual ledger must reset when core book expiry changes
INC-2026-021 | INC-2026-STAB-04 | WebSocket Previous Close frame treated as fatal error | 2026-06-12 | Observed 2026-06-12: WebSocket Previous Close frame treated as fatal error ¦ Root cause: Dhan v2 control frame without LTP triggered reconnect loop ¦ Fixed 2026-06-12: extract_ltp_from_ws_tick skips non-LTP control frames ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-021 | INC-2026-022 | DRISHTI cold-start without JWT + ATO pause/resume churn after false WS failover | 2026-06-25 | Observed 2026-06-25: Start All 10:43 without JWT until 10:44:52; false WS failover 10:46:05; ~25 min ATO pause/resume churn on nifty_ltp_feed_stale ¦ Root cause: Mid-session reconnect lacked transport grace (STAB-06 fix); on_feed_stale_cleared immediately resumed on brief fresh cache while REST was flaky ¦ Fixed 2026-06-25: Transport grace on reconnect + AUTO_RESUME_STABLE_SECONDS=45 sustained can_auto_resume_feed_recovery before auto-resume ¦ Validated: pytest test_feed_recovery sustained resume; Post-fix session no pause/resume churn in drishti logs ¦ Lesson: Never auto-resume ATO on first stale_cleared tick — require sustained trading-ready cache
INC-2026-022 | INC-2026-STAB-06 | WS 429 cooldown exceeded stale threshold → false failover | 2026-06-12 | Observed 2026-06-12: WS 429 cooldown exceeded stale threshold → false failover ¦ Root cause: Stale watchdog ignored rate_limit_until during cooldown ¦ Fixed 2026-06-12: Skip stale alerts during rate-limit cooldown; refresh last_update_at on 429 ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-022 | INC-2026-021 | JAGRAN Telegram publish timeout during morning feed incident | 2026-06-25 | Observed 2026-06-25: publish failed: Timed out at 10:50:54 IST during DRISHTI feed failover spam ¦ Root cause: Telegram API timeout while incident alerts flooded chat during WS/REST churn ¦ Fixed 2026-06-25: No code change — transient; feed stabilization + sustained auto-resume reduces alert volume ¦ Validated: JAGRAN logs post-11:15 show no further publish timeouts ¦ Lesson: Correlate JAGRAN timeouts with upstream feed incidents before chasing bot bugs
INC-2026-STAB-01 | INC-2026-STAB-02 | KAVACH menu reads wrong pause state in UAT | 2026-06-12 | Observed 2026-06-12: KAVACH menu reads wrong pause state in UAT ¦ Root cause: _read_algo_pause_reason() used default StateManager path ¦ Fixed 2026-06-12: Use state_path(workspace_root()) ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-02 | INC-2026-STAB-01 | UAT state-file split-brain — ATO pause written to wrong path | 2026-06-12 | Observed 2026-06-12: UAT state-file split-brain — ATO pause written to wrong path ¦ Root cause: pause_algo() used data/batman_state.json while UAT reads data/uat/batman_state.json ¦ Fixed 2026-06-12: default_state_path() → state_path(workspace_root()) mode-aware ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check ¦ Lesson: All cross-bot state writes must use state_path() — never hard-code data/
INC-2026-STAB-04 | INC-2026-017 | Mid-session WebSocket false failover — stale watchdog grace gap | 2026-06-25 | Observed 2026-06-25: WS connected at 10:46:02 then ATO auto-paused nifty_ltp_websocket_failed at 10:46:05 before first tick ¦ Root cause: Feed stale watchdog only applied 09:15 startup grace, not grace after mid-session WS reconnect when last_update_at is None ¦ Fixed 2026-06-25: mark_transport_started() + is_within_transport_grace() — 30s grace after WS connect / REST service start ¦ Validated: pytest test_feed_stale_watchdog_ws_transport_grace_after_reconnect ¦ Lesson: Transport-level grace must cover reconnect, not only market open
INC-2026-STAB-05 | INC-2026-STAB-06 | WS 429 cooldown exceeded stale threshold → false failover | 2026-06-12 | Observed 2026-06-12: WS 429 cooldown exceeded stale threshold → false failover ¦ Root cause: Stale watchdog ignored rate_limit_until during cooldown ¦ Fixed 2026-06-12: Skip stale alerts during rate-limit cooldown; refresh last_update_at on 429 ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check
INC-2026-STAB-06 | INC-2026-017 | Mid-session WebSocket false failover — stale watchdog grace gap | 2026-06-25 | Observed 2026-06-25: WS connected at 10:46:02 then ATO auto-paused nifty_ltp_websocket_failed at 10:46:05 before first tick ¦ Root cause: Feed stale watchdog only applied 09:15 startup grace, not grace after mid-session WS reconnect when last_update_at is None ¦ Fixed 2026-06-25: mark_transport_started() + is_within_transport_grace() — 30s grace after WS connect / REST service start ¦ Validated: pytest test_feed_stale_watchdog_ws_transport_grace_after_reconnect ¦ Lesson: Transport-level grace must cover reconnect, not only market open
INC-2026-STAB-06 | INC-2026-STAB-05 | WebSocket HTTP 429 reconnect storm | 2026-06-12 | Observed 2026-06-12: WebSocket HTTP 429 reconnect storm ¦ Root cause: 429 incremented failure counter → false failover ¦ Fixed 2026-06-12: 429 cooldown; do not increment consecutive_failures ¦ Validated: pytest stabilization subset; scripts/stabilization_verify.py; phase1_bot_check

## Lessons_Learned
incident_id | date_fixed | lesson
INC-2026-016 | 2026-06-25 | UAT fixture expiry must roll or block with clear operator message
INC-2026-016 | 2026-06-25 | Virtual ledger must reset when core book expiry changes
INC-2026-017 | 2026-06-25 | Transport-level grace must cover reconnect, not only market open
INC-2026-018 | 2026-06-25 | All agent diagnostic tools must be mode-aware
INC-2026-021 | 2026-06-25 | Correlate JAGRAN timeouts with upstream feed incidents before chasing bot bugs
INC-2026-022 | 2026-06-25 | Never auto-resume ATO on first stale_cleared tick — require sustained trading-ready cache
INC-2026-STAB-01 | 2026-06-12 | All cross-bot state writes must use state_path() — never hard-code data/

## Open_Only
incident_id | title | date_observed | date_fixed | status | severity | priority | robot | category | subsystem | what_was_the_issue | root_cause | how_we_solved_it | validation_evidence | related_incidents | commentary